## Slide 1
SDMX TECHNICAL WORKING GROUP
SDMX–DPM Interoperability
Work Package
Status Update — April 2026
Lead: Antonio Olleros (TWG)

## Slide 2
Work Plan — Status vs. Plan
Phase | Q4 2025 | Q1 2026 | Q2 2026 ★ | Q3 2026 | Status
1 – Consolidation | Done | Done | — | — | ✓ Complete
2 – Business Case | — | Done | Review | — | In progress
3 – Model Relationships | — | Done | Ongoing | Planned | In progress
4 – Transformation Guidance | — | — | Started | Planned | On schedule
5 – Website Publication | — | — | Planned | Planned | On schedule
★ = Current quarter (Q2 2026, April 2026) | Source: Concept Note, September 2025

## Slide 3
Deliverables — Status and Next Steps
Key achievements
Mapping rules documented for all major artefact types: glossary, data definition, tables/headers, and gaps
Business case draft complete: stakeholder value, use cases, scope and risks
Next steps
Complete model docs:
  versioning & extensibility
  gaps sections
Work on data instances (SDMX-CSV ↔ XBRL-CSV)
Transformation guidance
  Add scripts?
Deliverable | Status
Business case document | Draft complete – under review
Model relationship documentation | In progress – well advanced
Transformation guidance | Started – DPM→SDMX repo in place
Web-ready content / publication | Planned Q2–Q3 2026